## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | Study OWASP Top 10 guidelines & security standards for Python/Java | Must | None | Thimmampalli Asritha | Done
Sprint 1 | Sprint 1 | US-02 | Design FastAPI backend architecture, SQLAlchemy models and API router | Must | US-01 | Thimmampalli Asritha | Done
Sprint 1 | Sprint 1 | US-03 | Implement Code Submission Module (Paste & Upload endpoints) | Must | US-02 | Thimmampalli Asritha | Done
Sprint 1 | Sprint 1 | US-04 | Implement AST & Regex Language Auto-Detection for Python and Java | Must | US-03 | Thimmampalli Asritha | Done
Sprint 1 | Sprint 2 | US-05 | Build ChromaDB RAG Vector Knowledge Base with HuggingFace embeddings | Must | US-02 | Thimmampalli Asritha | Done
Sprint 2 | Sprint 2 | US-06 | Build Code Analysis Agent for quality, complexity & anti-patterns | Must | US-05 | Thimmampalli Asritha | Done
Sprint 2 | Sprint 3 | US-07 | Build Security Vulnerability Agent for OWASP Top 10 (CWE-798, CWE-89) | Must | US-06 | Thimmampalli Asritha | Done
Sprint 2 | Sprint 3 | US-08 | Build LangGraph multi-agent parallel execution orchestrator pipeline | Must | US-06, US-07 | Thimmampalli Asritha | Done
Sprint 2 | Sprint 3 | US-09 | Validate multi-agent pipeline using vulnerable sample code suites | Should | US-08 | Thimmampalli Asritha | Done
Sprint 3 | Sprint 3 | US-10 | Build Next.js Dashboard UI & Security Findings Display Panel | Must | US-08 | Thimmampalli Asritha | Done
Sprint 3 | Sprint 3 | US-11 | Implement RAG Assistant search interface & API vector store query endpoint | Should | US-10 | Thimmampalli Asritha | Done
Sprint 3 | Sprint 3 | US-12 | Implement PDF & HTML Executive Summary Report Generator | Could | US-10 | Thimmampalli Asritha | Done
Sprint 3 | Sprint 3 | US-13 | Build Remediation Agent for specific fix recommendations & corrected code snippets | Must | US-08 | Thimmampalli Asritha | Done
Sprint 3 | Sprint 3 | US-14 | Build PR Summary Agent for executive review overview, health score & prioritized roadmap | Must | US-13 | Thimmampalli Asritha | Done
Sprint 3 | Sprint 3 | US-15 | Build RAG Conversational Code Assistant interface & ChromaDB query integration | Must | US-10 | Thimmampalli Asritha | Done
Sprint 3 | Sprint 3 | US-16 | Implement PDF, Markdown, and JSON Export Module for code review reports | Must | US-14 | Thimmampalli Asritha | Done

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Day7 | Day8 | Day9 | Day10 | Day11 | Day12 | Day13 | Day14
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-01 | T-01 | Research OWASP Top 10 guidelines & security standards | 2026-07-01 | 2026-07-02 | Thimmampalli Asritha | Research | Done | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-02 | Design FastAPI backend architecture and DB schemas | 2026-07-02 | 2026-07-03 | Thimmampalli Asritha | Architecture | Done | 10 | 0 | 2 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-03 | Implement Code Submission Paste & Upload APIs | 2026-07-04 | 2026-07-05 | Thimmampalli Asritha | Development | Done | 12 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T-04 | Implement Python & Java AST language detector | 2026-07-06 | 2026-07-07 | Thimmampalli Asritha | Development | Done | 8 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T-05 | Setup ChromaDB vector store and HuggingFace embeddings | 2026-07-08 | 2026-07-10 | Thimmampalli Asritha | RAG Setup | Done | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 0
US-06 | T-06 | Implement Code Analysis Agent for quality & smells | 2026-07-11 | 2026-07-13 | Thimmampalli Asritha | AI Agent Dev | Done | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 0
US-13 | T-07 | Build Remediation Agent for fix recommendations & corrected code examples | 2026-07-25 | 2026-07-27 | Thimmampalli Asritha | AI Agent Dev | Done | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 0
US-14 | T-08 | Build PR Summary Agent for executive overview & health score calculation | 2026-07-28 | 2026-07-30 | Thimmampalli Asritha | AI Agent Dev | Done | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0
US-15 | T-09 | Develop Developer Review Portal UI with severity filter & interactive code viewer | 2026-07-31 | 2026-08-02 | Thimmampalli Asritha | Frontend Dev | Done | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7
US-15 | T-10 | Build RAG Conversational Code Assistant interface & ChromaDB query integration | 2026-08-03 | 2026-08-05 | Thimmampalli Asritha | RAG & Chat UI | Done | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
US-16 | T-11 | Implement PDF, Markdown, and JSON Code Review Report Generator & Export Endpoints | 2026-08-06 | 2026-08-07 | Thimmampalli Asritha | Reporting Dev | Done | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | FastAPI router duplicate endpoint registration | Cleaned router.py and removed duplicate route bindings
Sprint 1 | Day 3 | Anthropic API key dependency issue | Migrated orchestrator model calls to Google Gemini API
Sprint 2 | Day 5 | Missing virtual environment packages during setup | Updated requirements.txt and reinstalled backend venv
Sprint 2 | Day 8 | ChromaDB vector store timeout on RAG search | Fixed backend server connection and initialized embeddings
Sprint 3 | Day 10 | Next.js frontend connection refused on port 3000 | Started Next.js dev server (npm run dev) on port 3000
Sprint 3 | Day 12 | Remediation agent corrected code formatting for Python & Java | Integrated standardized language templates for parameterized queries
Sprint 3 | Day 13 | PR Summary Agent health score calculation precision across severities | Implemented weighted health score formula max(0, 100 - weighted_sum)
Sprint 3 | Day 14 | CORS preflight request blocked on frontend login endpoint | Added allow_origin_regex in FastAPI main.py to allow all localhost origins
Sprint 3 | Day 14 | Markdown and JSON export missing in report generator module | Added generate_submission_markdown and generate_submission_json methods and routes

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-07-01 | 2026-07-07 | Thimmampalli Asritha | Automated AST syntax checking | Hardcoding API endpoints | Writing modular agent code | Established centralized config.py
2 | Sprint 2 | 2026-07-08 | 2026-07-15 | Thimmampalli Asritha | Parallel LangGraph execution | Synchronous vector DB calls | Comprehensive unit testing | Implemented async ChromaDB retriever
3 | Sprint 3 | 2026-07-16 | 2026-07-24 | Thimmampalli Asritha | Full Milestone 3 multi-agent pipeline & export endpoints | Manual report formatting & unhandled CORS options | Automated testing with pytest & interactive developer portal | Completed Remediation Agent, PR Summary Agent, RAG Assistant & PDF/MD/JSON exports